DRILLING PROPOSAL OUTLINE DOCUMENT

Alpha-07 Well | Alpha Field | Central Sumatra Basin

CONFIDENTIAL  |  Document Code: DPM-2026-DP-ALPHA-07  |  Phase 1 — Gate 1 Sanction

EXECUTIVE SUMMARY

Structured with McKinsey Answer-First Framework: Answer → Reasoning → Evidence

1.  Project Mandate & Justification

→ ANSWER (Bottom Line Up Front) Core Energy Solution should sanction Alpha-07 to unlock stranded reserves in Alpha Field at a low-risk investment of USD 1.84 million, leveraging existing infrastructure and a proven development analog to deliver an incremental recovery of 0.58 MMBO.

Reasoning

Alpha Field is significantly under-developed relative to its resource base. With an OOIP of 21.66 MMSTB and cumulative production of only 6.48 MMSTB, the recovery factor stands at just 16.62%. The 5-well development program — anchored by Alpha-07 as the pilot well — provides a phased, capital-efficient pathway to improve recovery, supported by existing surface facilities and minimal new infrastructure requirements.

The directional J-type design avoids land acquisition complications posed by oil palm plantations, industrial forest zones, and densely populated areas above the target reservoirs, maximizing flexibility while minimizing ESIA exposure.

Evidence

- OOIP of 21.66 MMSTB with only 16.62% recovery factor — substantial upside remains

- Infill 5-well program projected to deliver ~0.58 MMBO incremental recovery through to 2041

- Alpha-07 utilizes existing Core Energy Solution surface facilities — no major new infrastructure required

- Directional J-type design minimizes surface footprint to 0.4–0.7 ha per wellpad

- Project aligns with SKK Migas production growth targets and Core Energy Solution asset optimization strategy

2.  Well Classification

→ ANSWER Alpha-07 is a Development Well — a directional J-type producer with cased-hole completion and ESP artificial lift — representing the lowest-risk execution path for Alpha Field.

Reasoning

The four target reservoirs (Bara, Bama, Raja, Prima sands) are fully delineated through prior drilling campaigns (Alpha-01 to Alpha-06), removing subsurface definition risk from the critical path. Classification as a development well rather than an exploratory or appraisal well reflects the high geological confidence and allows the team to focus execution risk management on operational variables such as wellbore stability, loss circulation, and cementing quality.

ESP installation is necessary to overcome the field-wide high water cut (~99%) and sustain economic production rates, while cased-hole completion preserves the option for selective perforation and future zone optimization across the commingled reservoir intervals.

Evidence

- 6 offset wells (Alpha-01 to Alpha-06) provide direct analog data for all target formations

- Reservoirs Bara, Bama, Raja, Prima previously demonstrated hydrocarbon productivity

- Cased-hole completion enables zonal selectivity across commingled intervals

- ESP specification: optimized per well depth, flow rate, and GOR; custom-manufactured with 16–24-week lead time

- Target reservoirs at ~4,042–4,676 ft TVD — within proven well-control competency window for 750 HP rig

3.  Success Criteria & KPIs

→ ANSWER Alpha-07 success is defined by three mutually reinforcing criteria: subsurface data capture, production rate confirmation, and cost discipline — all within a zero-LTI HSSE envelope.

Reasoning

Gate 1 sanction requires management confidence that the well will deliver both geological and commercial value. The success framework therefore spans technical data capture (to de-risk subsequent wells), production validation (to confirm the DCA-based reserve estimate), and cost control (to ensure the program remains investable). A failure on any single dimension would impair the business case for the follow-on 4-well development program worth approximately USD 7.4 million in total D&C expenditure.

Evidence

| KPI | Target | Rationale |
| --- | --- | --- |
| Planned Total Depth | ~5,000 ft MD | Penetrates all 4 target reservoir intervals |
| Initial Production (P50) | 132 BOPD | DCA analog-validated; P10–P90: 106–158 BOPD |
| Total Fluid Rate | 2,000 BFPD | ESP-supported; high WC field condition |
| Incremental Reserve (P50) | 156 MBO / well | EUR basis for 5-well program = ~0.58 MMBO |
| Well Cycle Time | 21.3–29.3 days | Rig move + drill + complete |
| NPT Target | <5–10% | Offset well lessons applied |
| AFE Overrun Tolerance | ≤10% | Max contingency USD 177,961 pre-approved |
| HSSE Target | Zero LTI / fatalities | SKK Migas & CES HSSE compliance |
| Logging Program | Triple combo + SWC | Full formation evaluation required for well 2–5 sanction |

4.  Executive Sanction Request

→ ANSWER Management is requested to approve three specific actions: (1) sanction execution of Alpha-07, (2) authorize USD 1.84M AFE plus USD 177,961 contingency, and (3) formally accept the defined risk envelope before proceeding to Gate 2.

Reasoning

Gate 1 sanction unlocks the critical path to Q4 2026 spud: LLI procurement for ESP (16–24-week lead), casing strings (12+ weeks), and tubing. Delay beyond Gate 1 approval will cascade directly into spud date and first oil. The risk profile is well-understood — 29 identified risks across subsurface, operational, and HSE domains, none rated Extreme — and all High-rated risks carry defined mitigation and contingency protocols. Management acknowledgement of the three High-rated subsurface risks (loss circulation, differential sticking, and surface leaking) is required to enable the execution team to mobilize resources proportionally.

Gate 2 transition will cover detailed engineering, PPFG calibration, final well design freeze, regulatory permit finalisation (PTD), and full procurement execution. Approval of this document constitutes the formal commercial mandate for that work.

Evidence

- Total AFE: USD 1,779,610 D&C + USD 177,961 contingency = USD 1,957,571 total approved budget envelope

- Risk summary: 0 Extreme, 7 High, 17 Medium, 5 Low — risk profile consistent with a mature development well

- Three High-rated subsurface risks requiring management acknowledgement: Loss Circulation (Likelihood 4), Differential Sticking (Likelihood 3), Surface Leaking (Likelihood 3)

- Critical path: Gate 1 approval required no later than Q2 2026 to protect Q4 2026 spud date (1 November 2026 target)

- LLI Procurement: ESP (16–24 wks), 7" Casing ×140 jts, 9-5/8" Casing ×48 jts, 3½" Tubing ×161 jts — all Critical Category LLI

- AFE drawdown authority: Drilling Supervisor (up to 5%), Project Manager (5–10%), Management Committee re-authorization (>10%)

- Prepared by PMT Group 6 Core Energy Solution; reviewed by Technical Committee; approval requested from General Chairman

AT-A-GLANCE: ALPHA-07 WELL SUMMARY

| TECHNICAL SNAPSHOT | COMMERCIAL SNAPSHOT |
| --- | --- |
| Well Type: Directional J-type Producer Rig: 750 HP Land Rig Target TD: ~5,312 ft MD Targets: Bara, Bama, Raja, Prima sands Completion: Cased-hole + ESP Cycle Time: 21.3–29.3 days Target Spud: 1 November 2026 | Total AFE (incl. contingency): USD 1.96 M Base D&C Cost: USD 1.78 M Contingency: USD 178 K (10%) Incremental Reserve (P50): 156 MBO / well 5-Well Program Reserve: ~0.58 MMBO to 2041 IP Rate (P50): 132 BOPD Field OOIP / RF: 21.66 MMSTB / 16.62% |